## README
Project Management Plan: input workbook
SAMPLE version: every tab holds example rows for a made-up highway project. Delete them before you enter your own data.
How to use
1. Fill in the Project Info tab, then the plan tabs and the tool tabs. Leave a tab empty if you have nothing for it.
2. On the Project Management Plan page press Import from Excel (.xlsx) and choose this file. The plan fills itself; the page lists the tabs it will replace and asks first.
3. Export to Excel (.xlsx) on the plan page downloads the current plan as a workbook like this one. Create Project Folder writes the 7 tool tabs as CSV files for the tools.
4. Keep one workbook for each project, and import the version you last edited.
Rules
Do not rename tabs and do not change or move the heading row (row 1) of any tab. The loader finds data by tab name and heading.
Dates: type them as yyyy-mm-dd (for example 2026-04-24). The date columns are already formatted that way.
Dropdown columns (status, priority, category, type, discipline) accept only the listed values.
Columns that the tools calculate themselves are left out: risk Score and Level, Cumulative Contract Value, and the Status of RFIs and correspondence. The tools work them out after import.
Cash Flow periods are text such as Jul-26. Keep that format.
Pictures (logo, signature, figures) cannot be held in Excel. Add them on the plan page.
Do not leave a row half empty in the middle of a table; blank rows at the end are ignored.
Tab | What it holds | Where the data goes
Project Info | Project, company, document and approval details | Cover and document control pages; fills the header of every tool
Narratives | The written boxes (scope, exclusions, protocol, HSE and so on) | Plan sections 2, 6, 7, 9, 10 and the Important Notice
Annexures | Titles and notes for the annexure pages | Annexure pages of the plan document
Revision History | Page: Document Control. One line per issue of the plan. | Plan page and 00_PMP/01_*.csv
Issue Register | Page: Document Control. Who received the plan. | Plan page and 00_PMP/02_*.csv
Deliverables | Section 2.3. Dates also build the milestone list (3.1) and the Gantt starter rows. | Plan page and 00_PMP/03_*.csv
Discipline Matrix | Section 2.3. Put Yes where a discipline submits that document type. | Plan page and 00_PMP/04_*.csv
Internal Deliverables | Section 3.3. | Plan page and 00_PMP/05_*.csv
Budget & Billing | Sections 4.1-4.3. Billing dates and amounts become the Cash Flow planned column. | Plan page and 00_PMP/06_*.csv
Personnel | Section 5.1. | Plan page and 00_PMP/07_*.csv
Mobilisation | Section 5.2. Also becomes Gantt starter rows. | Plan page and 00_PMP/08_*.csv
Task Assignments | Section 5.3. Also becomes Gantt starter rows. | Plan page and 00_PMP/09_*.csv
Input Review | Section 6.1. | Plan page and 00_PMP/10_*.csv
Output Review | Section 6.2. | Plan page and 00_PMP/11_*.csv
Verification | Section 6.3. | Plan page and 00_PMP/12_*.csv
Contacts | Section 7.1. | Plan page and 00_PMP/13_*.csv
Procurement | Section 8.1. | Plan page and 00_PMP/14_*.csv
Sub-consultants | Section 8.2. | Plan page and 00_PMP/15_*.csv
Requirements | Section 10.1. | Plan page and 00_PMP/16_*.csv
Assumptions | Section 1.1. | Plan page and 00_PMP/17_*.csv
KPIs | Section 1.2. | Plan page and 00_PMP/18_*.csv
Baselines | Section 2.8. | Plan page and 00_PMP/19_*.csv
Change Approvals | Section 2.9.1 (with the change control procedure text). | Plan page and 00_PMP/20_*.csv
Reporting Plan | Section 7.3. | Plan page and 00_PMP/21_*.csv
01 Gantt | Design and Construction Gantt Chart | 01_Gantt_Schedule/gantt_activities.csv
02 Risks | Risk Register and Risk Matrix | 02_Risk_Register/risk_register.csv
03 Actions | Action and Minutes of Meeting Tracker | 03_Action_Minutes/action_items.csv
04 Variations | Change Order / Variation Order Register | 04_Variation_Orders/variation_orders.csv
05 Cash Flow | Cash Flow and S Curve Calculator | 05_Cash_Flow/cash_flow.csv
06 Correspondence | Project Correspondence Register | 06_Correspondence/correspondence_register.csv
07 RFI | RFI / Technical Query Tracker | 07_RFI_Tracker/rfi_register.csv
Gantt tab
Put your full activity list on the 01 Gantt tab: No. is the WBS number (1, 1.1, 1.2), a row without dates is read as a heading, Predecessors use Code:Type:Lag (for example 1.2:FS:0). If the tab is empty, the page builds starter rows from your deliverables, mobilisation and tasks instead. Duration, when given, decides the end date.

## Project Info
Key | Field | Value | Note
name | Project Name | Sample Highway Rehabilitation Project | Fills the project name in every tool.
client | Client / Owner | Sample Roads Authority | Fills the client in every tool.
clientAddr | Client address / contact | Sample Roads Authority, 1 Example Road, Sample City
clientRef | Client Reference No. | SRA/2026/014
internalRef | Internal Reference / Project No. | PRJ-1042
contract | Contract No. | C-2026-014 | Fills the Cash Flow tool.
opportunity | Opportunity number (if any) | OPP-2025-117
contractType | Contract type | Lump sum (fixed fee)
fee | Project fee value | USD 545,000 | Write it as CURRENCY amount, e.g. USD 545,000, so the Variation and Cash Flow tools can read currency and value.
location | Location | Sample City
pm | Project Manager | A. Project Manager
director | Project Director | D. Director
award | Date of award | 2026-01-05 | yyyy-mm-dd
start | Start date | 2026-01-12 | yyyy-mm-dd
end | Completion date | 2026-12-18 | yyyy-mm-dd
date | Date of Plan | 2026-10-04 | yyyy-mm-dd
rev | Revision | 0
prep | Prepared By | A. Project Manager | Fills Prepared By in the tools.
docType | Document type | Project Management Plan
fileLoc | File location | Project folder / 01 Management / Project Management Plan
owner | Document ownership | The client owns this document unless the contract states otherwise.
company | Company name | Sample Engineering Consultants
coAddr | Company address | 10 Sample Street, Sample City
coPhone | Phone | +00 000 000 0000
coEmail | Email | info@example.com
coWeb | Website | www.example.com
approved | Approved By | D. Director
approverTitle | Position | Director
approverPhone | Phone | +00 000 000 0001
approverEmail | Email | director@example.com
approvedDate | Approval date | 2026-01-15 | yyyy-mm-dd
description | Project description | Rehabilitation of a 24 km two-lane highway section in Sample City, including pavement strengthening, drainage upgrade and road safety improvements. The client is the Sample Roads Authority and the works are procured under a single construction contract.
objective | Project objectives | Rehabilitate 24 km of two-lane highway: pavement design, drainage upgrade and construction supervision. Success means the road is opened on time, within budget and without lost-time injuries.

## Revision History
Rev. | Date | Description of change | Prepared by | Reviewed by | Approved for issue by
0 | 2026-01-15 | Issued for approval | A. Project Manager | D. Director | D. Director

## Issue Register
No. | Issued to | Organisation | Date issued | Copies
IS-01 | E. Client | Sample Roads Authority | 2026-01-16 | 1
IS-02 | Project file | Sample Engineering Consultants | 2026-01-16 | 1

## Deliverables
No. | Contract deliverable | Responsible | Due date | Status
D-01 | Inception report | Project Manager | 2026-02-13 | Done
D-02 | Preliminary design report | Lead Engineer | 2026-04-24 | In progress
D-03 | Detailed design drawings and bill of quantities | Lead Engineer | 2026-07-10 | Not started
D-04 | Tender documents | Contracts Engineer | 2026-08-14 | Not started

## Discipline Matrix
Discipline | Design scope | Design Basis | Drawings | BOQ | Specifications | Design Report
Roads | Mainline, junctions, pavement | Yes | Yes | Yes | Yes | Yes
Drainage | Culverts, side drains, outfalls | Yes | Yes | Yes | Yes | Yes
Structures | Retaining walls, minor bridges | Yes | Yes | Yes |  | Yes

## Internal Deliverables
No. | Internal deliverable | Owner | Due date | Status
I-01 | Internal review of preliminary design | Technical Reviewer | 2026-04-10 | In progress
I-02 | Quantity take-off check | Senior Engineer | 2026-06-26 | Not started

## Budget & Billing
No. | Budget item | Budget | Planned billing date | Billing amount | Notes
B-01 | Design phase | 180000 | 2026-07-31 | 180000 | Lump sum
B-02 | Tender support | 45000 | 2026-09-30 | 45000
B-03 | Supervision (monthly) | 320000 | 2026-12-18 | 320000 | 12 months

## Personnel
No. | Role | Name | Responsibilities | Allocation | From | To
P-01 | Project Manager | A. Project Manager | Overall delivery, client interface, plan owner | 40% | 2026-01-12 | 2026-12-18
P-02 | Lead Engineer | B. Engineer | Design lead and technical sign-off | 80% | 2026-01-12 | 2026-08-14
P-03 | Resident Engineer | C. Supervisor | Site supervision and reporting | 100% | 2026-09-01 | 2026-12-18

## Mobilisation
No. | Mobilisation activity | Responsible | Planned date | Status
M-01 | Kick-off meeting with client | Project Manager | 2026-01-16 | Done
M-02 | Set up project folders and document control | Document Controller | 2026-01-20 | Done

## Task Assignments
Task no. | Task | Assigned to | Budget hours | Due date | Status
T-01 | Pavement structural design | B. Engineer | 320 | 2026-05-29 | In progress
T-02 | Drainage hydraulic design | D. Hydrologist | 240 | 2026-06-12 | Not started

## Input Review
No. | Input data / document | Source | Reviewer | Date reviewed | Result
IN-01 | Topographic survey, chainage 0 to 24 km | Survey sub-consultant | B. Engineer | 2026-02-20 | Reviewed - OK
IN-02 | Traffic count data | Client | B. Engineer | 2026-03-02 | Issue raised

## Output Review
No. | Output / deliverable reviewed | Reviewer | Date | Result
OR-01 | Inception report | Technical Reviewer | 2026-02-11 | Verified

## Verification
No. | Item to verify | Method | Verifier | Planned date | Status
V-01 | Pavement design calculations | Independent review | Technical Reviewer | 2026-05-08 | Not started
V-02 | Bill of quantities | Peer review | Senior Engineer | 2026-07-03 | Not started

## Contacts
No. | Group | Role | Name | Organisation | Email | Phone
C-01 | Client | Client Representative | E. Client | Sample Roads Authority | client@example.com | +00 000 0000
C-02 | Internal | Project Manager | A. Project Manager | Sample Engineering Consultants | pm@example.com | +00 000 0001

## Procurement
No. | Item / service to procure | Type | Method | Needed by | Status
PR-01 | Topographic survey | Sub-consultant | Quotation (3 bids) | 2026-01-30 | Done
PR-02 | Pavement design software licence | Software | Direct purchase | 2026-03-01 | Not started

## Sub-consultants
No. | Sub-consultant / supplier | Scope of agreement | Value | Agreement date | Status
SC-01 | Survey Co. | Topographic survey of full corridor | 28000 | 2026-02-02 | Signed

## Requirements
No. | Requirement / manual | Issued by | Applies to | Status
R-01 | Client design manual, latest edition | Client | All design deliverables | Received
R-02 | Environmental permit conditions | Environmental authority | Drainage design and construction | Pending

## Assumptions
No. | Type | Description | Impact if wrong / effect | Owner | Status
AC-01 | Assumption | The topographic survey is received by week 4 | Pavement design starts late; milestones move | Client | Open
AC-02 | Assumption | Existing drainage drawings are reliable | Extra site checks and redesign | Lead Engineer | Open
AC-03 | Constraint | Road works only in the dry season (October to April) | Fixed construction window | Project Manager | Accepted
AC-04 | Constraint | One lane must stay open to traffic at all times | Works in short sections; slower progress | Client | Accepted

## KPIs
No. | KPI | Measure | Target | Source | Frequency | Responsible
K-01 | Schedule | Schedule performance index (SPI) | >= 0.95 | Earned Value Management | Monthly | Project Manager
K-02 | Cost | Cost performance index (CPI) | >= 0.95 | Earned Value Management | Monthly | Project Manager
K-03 | Deliverables on time | Share of deliverables issued by their due date | >= 90% | 2.3 Contract Deliverables | Monthly | Lead Engineer
K-04 | Quality | NCRs closed within 14 days | >= 90% | NCR Quality Control Tracker | Monthly | QA Manager
K-05 | Safety | Lost-time incidents | 0 | Safety / HSE Dashboard | Monthly | HSE Officer
K-06 | Client satisfaction | Client survey score | >= 4 of 5 | Closeout survey | At handover | Director

## Baselines
No. | Baseline | Reference document | Rev. | Approved by | Date approved
BL-01 | Scope | Section 2 Scope of Work and the WBS (2.5) | 0 | Client Project Manager | 2026-01-15
BL-02 | Schedule | Design and Construction Gantt Chart (annexure) | 0 | Client Project Manager | 2026-01-15
BL-03 | Cost | Budget and Billing Schedule (4.1-4.3) | 0 | Director | 2026-01-15

## Change Approvals
No. | Change size (cost / time effect) | Approved by | Notes
CA-01 | Under USD 10,000 and under 7 days | Project Manager | Reported in the next monthly report
CA-02 | Up to USD 50,000 or up to 30 days | Project Director | Within 5 working days
CA-03 | Above USD 50,000, over 30 days, or any change of scope | Client | Formal variation order

## Reporting Plan
No. | Report / meeting | Purpose | Prepared / chaired by | To / attendees | Frequency | Due / day | Source tool
RM-01 | Monthly progress report | Progress, earned value, risks and issues | Project Manager | Client Project Manager, Director | Monthly | By the 5th | Gantt Chart, EVM
RM-02 | Progress meeting | Review progress, actions and decisions | Project Manager | Client, contractor | Weekly | Monday | Action / MOM Tracker
RM-03 | Internal team meeting | Coordinate the work and resources | Project Manager | Project team | Weekly | Thursday | Action / MOM Tracker
RM-04 | Risk review | Update the risk register and actions | Project Manager | Team leads | Monthly | Last Friday | Risk Register
RM-05 | HSE report | Incidents, inspections and statistics | HSE Officer | Project Manager, client | Monthly | By the 5th | Safety / HSE Dashboard
RM-06 | Design review | Check the design at each stage | Lead Engineer | Client, design team | At milestones | 30 / 60 / 90%

## Narratives
Key | Section | Text
controlstmt | Controlled copy statement | The controlled copy of this plan is the latest revision held in the project folder. Printed or emailed copies are uncontrolled: check the revision number against the project folder before relying on them.
approvalstmt | Approval statement | This Project Management Plan has been prepared by {company} for {project name}. It is approved for use on the project by the person named below and is reviewed at least every [six] months, and whenever the scope, programme or organisation changes significantly. Each revision is recorded in the Revision History.
notice | Important Notice | This document is confidential and is provided for the purpose of managing and controlling the project named on the cover. It is limited to the matters stated in it and must be read as a whole. It supersedes earlier drafts and is not updated for events after its date unless a new revision is issued. No person other than the client named on the cover may rely on it. Replace this wording with your organisation's standard notice.
scope | 2.1 Scope of Works | Detailed design of pavement rehabilitation and drainage improvements for 24 km. Tender documents and tender evaluation support. Full-time construction supervision and contract administration.
exclusions | 2.2 Exclusions | Land acquisition and utility relocation design. Traffic management design outside the project limits. Operation and maintenance after the defects liability period.
chgproc | 2.9 Change Control Procedure | Every change to scope, time or cost follows these steps: 1. Anyone may raise a change. It is logged in the Scope Change / Variation Register (2.7) with a number and date. 2. The project manager assesses its effect on scope, schedule, cost, quality and risk within 5 working days. 3. The change is approved or rejected by the person named in the approval limits below. No work on a change starts before approval. 4. Approved changes update the baselines (2.8), the programme and the budget; the revision is recorded. 5. The team and the client are told of the decision, and the register is closed out.
ex_eng | 6.5.1 Project Execution: Engineering / Design | Design follows the client design manual. Each drawing and calculation is checked by a second engineer before issue. Design reviews are held at 30%, 60% and 90% completion; comments are closed out before the next stage.
ex_is | 6.5.2 Project Execution: Information Systems Development and Deployment | Not applicable: the project has no software or systems work. Survey and design data are kept in the project folder structure in 7.3.
ex_con | 6.5.3 Project Execution: Construction | The resident engineer and two inspectors supervise the works full time. Every work package is inspected against the approved drawings and specifications before it is covered up. Test results and site instructions are logged daily.
ex_com | 6.5.4 Project Execution: Commissioning, Systemization and Startup | Each road section is handed over after a joint inspection with the client and the contractor. Defects found are listed and closed out before the taking-over certificate is issued.
ex_om | 6.5.5 Project Execution: Operation and Maintenance (O&M) | The contractor provides an operation and maintenance manual for drainage and road furniture before taking-over. Defects reported during the 12-month defects liability period are inspected and recorded.
protocol | 7.2 Project Communications Protocol | All formal correspondence goes through the document controller and is logged the same day. The client is answered within 5 working days. Weekly progress meeting on Mondays; minutes issued within 2 days.
filestruct | 7.5 File Structure and Document Control | Folders: 01 Contract, 02 Design, 03 Reports, 04 Correspondence, 05 Meetings. File name: Project-Discipline-Number-Title-Rev. Drafts are marked D, issued files are marked with a revision letter.
admin | 7.6 General Administration | Timesheets are submitted weekly and approved by the project manager. Invoices go to the client monthly, with the progress report attached. Leave and site travel are agreed with the project manager in advance.
hsemp | 9.2 Health, Safety and Environmental Management Plan (HSEMP) | The contractor submits a health and safety plan before mobilisation; the consultant reviews it and audits it monthly. All site staff attend a safety induction. Incidents and near misses are reported within 24 hours.
envplan | 9.4 Environmental Management and Sustainability | Works follow the environmental permit conditions. Dust, noise and run-off are checked weekly at sensitive locations. Excavated pavement material is reused in the sub-base where tests allow.
perf | 10.1.1 Performance Evaluation | The contractor's performance is scored quarterly on quality, time, safety and cooperation. Results are shared with the contractor and the client.
demob | 10.1.2 Project Completion and Demobilisation Plan | Site offices are cleared within 4 weeks of taking-over. Final records, as-built drawings and the project file are handed to the client at closeout.
intl | 10.1.3 International Issues | Not applicable: all work is in one country. Imported materials follow the client's procurement rules.
addreq | 10.1.4 Additional Requirements / Registers | The client's quality manual and the environmental permit are listed in the register in 10.1. New client requirements are added to the register when received.

## Annexures
Title | Source tool | Note
Design and Construction Gantt Chart | Design and Construction Gantt Chart | Project programme.
Risk Register and Risk Matrix Template | Risk Register and Risk Matrix Template | Current risk register and matrix.

## 01 Gantt
No. | Activity | Start Date | End Date | Duration | % Complete | Predecessors
1 | Contract deliverables | 2026-01-12 | 2026-08-14
1.1 | Inception report | 2026-01-12 | 2026-02-13 |  | 100
1.2 | Preliminary design report | 2026-01-12 | 2026-04-24 |  | 0
1.3 | Detailed design drawings and bill of quantities | 2026-01-12 | 2026-07-10 |  | 0
1.4 | Tender documents | 2026-01-12 | 2026-08-14 |  | 0
2 | Internal deliverables | 2026-01-12 | 2026-06-26
2.1 | Internal review of preliminary design | 2026-01-12 | 2026-04-10 |  | 0
2.2 | Quantity take-off check | 2026-01-12 | 2026-06-26 |  | 0
3 | Mobilisation | 2026-01-05 | 2026-01-20
3.1 | Kick-off meeting with client | 2026-01-05 | 2026-01-16 |  | 100
3.2 | Set up project folders and document control | 2026-01-05 | 2026-01-20 |  | 100
4 | Task assignments | 2026-01-12 | 2026-06-12
4.1 | Pavement structural design | 2026-01-12 | 2026-05-29 |  | 0
4.2 | Drainage hydraulic design | 2026-01-12 | 2026-06-12 |  | 0

## 02 Risks
Phase | Risk Description | Category | Likelihood | Impact | Mitigation | Owner | Status
Design | Topographic survey delayed, holding up the start of pavement design | Schedule | 3 | 4 | Request the survey early; agree an interim data cut-off with the client | A. Project Manager | Open
Design | Unforeseen subgrade conditions along the corridor | Geotechnical | 3 | 5 | Add test pits at 500 m spacing; allow a design contingency | B. Engineer | Open
Construction | Traffic accidents inside the work zones during rehabilitation | Safety (HSE) | 2 | 5 | Approved traffic management plan; daily site inspections | C. Supervisor | Open

## 03 Actions
Ref No. | Action Item | Raised By | Responsible | Due Date | Priority | Status | Remarks
A-01 | Confirm design standards and criteria with the client | E. Client | A. Project Manager | 2026-02-06 | High | Open
A-02 | Sign the survey sub-consultant agreement | A. Project Manager | Contracts Engineer | 2026-01-30 | Medium | Completed
A-03 | Submit the revised programme to the client | E. Client | A. Project Manager | 2026-03-13 | Medium | In Progress

## 04 Variations
VO No. | Description | Status | VO Value | Date Raised | Approval Date | Time Impact (d)
VO-01 | Additional culvert at km 12+300 | Approved | 12000 | 2026-04-06 | 2026-04-20 | 5
VO-02 | Extra pavement coring and testing | Submitted | 8500 | 2026-05-04 |  | 0
VO-03 | Additional geotechnical investigation | Proposed | 15000 | 2026-05-18 |  | 7

## 05 Cash Flow
Period | Planned Expenditure | Actual Expenditure
Jul-26 | 180000
Sep-26 | 45000
Dec-26 | 320000

## 06 Correspondence
No. | Ref No. | Type | Subject | From | To | Date | Response Due | Response Date | Remarks
1 | L-001 | incoming | Notice to proceed | Client | Consultant | 2026-01-12
2 | L-002 | outgoing | Submission of inception report | Consultant | Client | 2026-02-13 | 2026-02-27
3 | L-003 | incoming | Comments on inception report | Client | Consultant | 2026-02-24

## 07 RFI
No. | RFI Ref No. | Discipline | Subject / Query | Raised By | Assigned To | Date Raised | Priority | Response Due | Response Date | Remarks / Response
1 | RFI-001 | Civil | Confirm the design vehicle for pavement design | B. Engineer | E. Client | 2026-03-02 | High | 2026-03-09
2 | RFI-002 | Civil | Confirm the outfall location at km 8+400 | B. Engineer | E. Client | 2026-03-10 | Medium | 2026-03-17
3 | RFI-003 | Structural | Retaining wall surcharge loading criteria | B. Engineer | E. Client | 2026-03-16 | Low | 2026-03-30

## Lists (hidden)
Design and Construction Gantt Chart
Schedule Delay Analysis Tool
Action and Minutes of Meeting Tracker
Action / Responsibility Matrix
Change Order / Variation Order Register
Claims & EOT Register
Cash Flow and S Curve Calculator
Earned Value Management
Resource Loading Histogram
NCR Quality Control Tracker
Submittal Approval Tracker
RFI / Technical Query Tracker
Project Correspondence Register
Risk Register and Risk Matrix Template
Safety / HSE Dashboard
Permit & NOC Tracker
Project Health Board
Lessons Learned Register
Project Closeout & Handover Tracker
Contractor Performance Evaluation Dashboard